## 0. References & Citations
References & Citations — Master Registry
Every finding cites these. Design sources are the board's own released design data (a content fingerprint fixes the exact object reviewed). Standards are cited by standard number, and current editions were consulted in full for this review.
A · DESIGN SOURCE DATA (the board's own released files)
ID | Artifact | Fingerprint / note
S1 | Released BOM (mfr/MPN/package) | fingerprint 11d508a117
S2 | Released NC-drill, plated (Excellon tool table) | fingerprint a473e9bd24
S3 | Released NC-drill, non-plated | fingerprint ec887e56de
S4 | Field-solver stack-up / material model | fingerprint 49a35ce89b
S5 | Released placement list (X/Y/side/mount) | fingerprint 1c0c00196e
S6 | ODB++ CAD netlist (IPC-D-356 equivalent) | fingerprint d8913714b9
S7 | ODB++ eda/data (net records) | fingerprint 63e1079db4
S8 | Solder-paste layer — TOP (double-sided proof) | fingerprint 9b2526d01c
S9 | Solder-paste layer — BOTTOM | fingerprint e8ab351c30
S10 | Copper artwork set, 10 layers | 10 files
S11 | Native board record (layer stack) | binary
S12 | Native board record (finished thickness) | 1.6 mm
S13 | Evidence-recovery analysis (OCR of drawings) | internal analysis
S14 | DFM/DFA engineering reviews | internal analysis
B · STANDARDS APPLIED IN THIS REVIEW
Standard | Title / scope of use | Use in this review
IPC-2221 | Generic Standard on Printed Board Design | applied
IPC-2223 | Sectional Design Standard for Flex / Rigid-Flex | applied
IPC-2226 | Design Standard for HDI Boards (used to confirm NO HDI) | applied
IPC-2152 | Current-Carrying Capacity in PCBs | applied
IPC-7351 | Land-Pattern / Footprint Standard | applied
IPC-7525 | Stencil Design Guidelines (aperture area ratio ≥0.66) | applied
IPC-A-610 | Acceptability of Electronic Assemblies | applied
IPC-A-600 | Acceptability of Printed Boards | applied
IPC-7093 | Design/Assembly for Bottom-Termination Components (QFN) | applied
IPC-9252/D-356 | Electrical Test of Unpopulated Boards / netlist access | applied
IPC-7711/7721 | Rework, Modification and Repair | applied
J-STD-001 | Requirements for Soldered Electrical/Electronic Assemblies | applied
IPC-6012 | Qualification & Performance for Rigid PCBs (aspect ratio, hole-wall, warpage) | applied
IPC-7095 | Design & Assembly Implementation for BGAs (HIP, void, X-ray) | applied
IPC-4761 | Protection of Via Structures (fill / plug / cap) | applied
JEDEC J-STD-020 | Moisture/Reflow Sensitivity Classification (MSL) | applied
J-STD-033 | Handling/Packing of Moisture-Sensitive Devices (floor life, bake) | applied
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: the board's own released design package at baseline rev ACB_0001_2 — items S1–S14 in section A above (content fingerprints fix the exact objects reviewed).
Standards: current editions of the IPC and JEDEC standards listed in section B, applied per finding across this workbook.
Internal storage locations are omitted by design; artifacts are identified by content fingerprint only.

## 1. Document Control
Preliminary DFM / DFA Risk Screening — Document Control
Document type | Preliminary DFM/DFA Risk Screening — NOT a Manufacturing Release Review
Product | Open-hardware GNU/Linux PowerPC Notebook motherboard (ACube "PORTATILE")
Main processor | NXP T2080 QorIQ (quad e6500), U1, MPN T2080NXN8PTB, PBGA896
Design baseline reviewed | Xpedition project "Mas100n3 ACB_0001_2" (board file Mas100n3 ACB_0001_2.pcb)
Fabrication data date | NC-drill header: Mon Aug 08 2022 (ThruHolePlated.ncd)
Hardware / PCB revision | ACB_0001_2 (rev 2). Earlier rev ACB_0001_0 (rev 0) also present — NOT reviewed here
Schematic revision | PPC_PORTABILE R_0 (per Gerber .dsn reference) — CONFIRM against released schematic
BOM revision | PORTATILE_1_1_BOM_NEW_DEF.ods (rev 1.1) — 268 lines, 2,047 placements
Reviewing organisation | Product Engineer LLC
Review scope | PCB fabrication DFM + PCBA process DFM + DFA + DFT screening from released CAD/fab data
Excluded scope | Fabricator DFM sign-off; CM stencil/process review; pilot-build yield data; SI/PI sign-off; mechanical CAD tolerance run; component-level reliability
Standards referenced | IPC-2221/2222/2226, IPC-6012, IPC-A-600, IPC-7351, IPC-A-610, J-STD-001, IPC-7095, IPC-7093, IPC-2152, IPC-7525, IPC-4761, IPC-9252/D-356, IPC-7711/7721, JEDEC J-STD-020, J-STD-033 (revisions to be fixed at release)
Evidence rule | Every quantitative claim traces to a named source file + object/coordinate. Unknowns are marked NOT-IN-DATA, not assumed.
Maturity statement | Initial risk screening only. Quantitative fab/assembly analyses, supplier sign-off and build validation are NOT complete. Do not treat as an approval.
Change history | Rev A — initial release of this screening tracker.
Prepared by / date | Product Engineer LLC · see Final Gate sheet for signatures (open)
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S2] NC drill — plated (tool table) · [S4] Field-solver stack-up/material · [S5] Placement list (X/Y/side/mount) · [S6] ODB++ CAD netlist (access pts) · [S11] Altium board record (LayerStack)
Standards: IPC-2221 · IPC-2223 · IPC-2226 · IPC-2152 · IPC-7351 · IPC-7525 · IPC-A-610 · IPC-A-600 · IPC-7093 · IPC-9252/D-356 · IPC-7711/7721 · J-STD-001 · IPC-6012 · IPC-7095 · IPC-4761 · JEDEC J-STD-020 · J-STD-033
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 2. Executive Decision
Executive Release Decision — Gate-Separated Disposition
A single verdict is NOT used. Each decision is dispositioned separately against its blocking findings.
OVERALL DISPOSITION
Prototype fabrication/build may proceed ONLY after closure of the defined pre-build blockers below. NOT approved for production release. This package is a preliminary risk screening, not a manufacturing release review.
Decision | Disposition | Blocking findings | Basis
Design ready for engineering prototype | CONDITIONAL | DFM-01,03,05,06; DFA-02,03 | Layout is coherent; blocked by open pre-build fab/process items
Data package ready for PCB quotation | NO | DFM-01,05,08 | No released fab drawing / stack-up / finish; fabricator cannot quote to spec
Data package ready for PCB fabrication | NO | DFM-01,02,03,05,06,08 | Fab-doc package, finish, aspect-ratio & via-in-pad sign-off, panel all open
PCBA process ready for prototype | CONDITIONAL | DFA-01,03,04; DFM-07 | Buildable at low volume once stencil/MSL/X-ray/panel process defined
Design ready for pilot production | NO | All High + DFT-01 + build data | No supplier sign-off, no measured yield, no process capability
Design ready for volume production | NO | All High + build validation | Requires fab package, supplier qual, pilot yield, capability study
MINIMUM PRE-BUILD BLOCKERS (must close before prototype fabrication)
1. Confirm fabrication stack-up (ordered build, core/prepreg, Tg/Td/CAF, finished thickness ±tol).
2. Select and document PCB surface finish via trade study; obtain fab + CM approval (do NOT default to ENIG).
3. Confirm via & finished-hole construction; fab sign-off of 0.20 mm min drill / 8:1 (drill) ~10.7:1 (finished) aspect ratio.
4. Confirm BGA via-in-pad treatment for U1 (tented/plugged/filled/capped) — status NOT in data; confirmation required.
5. Release fabrication drawing (thickness, IPC class, finish, tolerances, impedance table).
6. Complete fabricator DFM and PCB supplier capability match.
7. Complete assembler stencil / paste / reflow / MSL process review.
8. Establish component MSL handling requirements (J-STD-033) — no MSL data in BOM.
9. Resolve BOM/AVL questions (3 lines missing MPN; single-source; no alternates/approval status).
10. Define inspection and test acceptance criteria (SPI/AOI/X-ray/ICT/FT).
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S2] NC drill — plated (tool table) · [S4] Field-solver stack-up/material · [S5] Placement list (X/Y/side/mount) · [S6] ODB++ CAD netlist (access pts) · [S13] Evidence-recovery memo (OCR) · [S14] DFM/DFA reviews
Standards: IPC-6012 · IPC-7095 · IPC-4761 · IPC-7525 · J-STD-033 · JEDEC J-STD-020
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 3. Scoring Rubric
Risk Scoring Rubric, Action Priority & Override Rules
Defines what each score means, how Action Priority is set (severity-first), and the release-gate override rules. Scores are readiness/risk, NOT design quality.
Score | Meaning (readiness/risk maturity) | Gate implication
1 | Verified — checked against source data & supplier capability; meets acceptance criteria | Pass
2 | Minor risk — small gap, low-effort closure, no supplier dependency | Pass w/ note
3 | Moderate — engineering exists but not released/verified; needs documentation or analysis | Conditional
4 | High — missing input, unverified critical characteristic, or supplier-dependent | Blocks pre-build
5 | Not ready / unknown critical characteristic — treated as OPEN risk, never neutral | Blocks release
SEVERITY-FIRST ACTION PRIORITY (S,O,D each 1–10; AP = High/Medium/Low)
Rating | Severity (S) | Occurrence (O) | Detection (D)
9–10 | Safety / total loss of function / field failure | Frequent / near-certain at this maturity | Cannot detect before release
6–8 | Major function or yield loss; scrap | Likely without control | Detectable only late (after build)
3–5 | Moderate; rework or cost | Occasional | Detectable in process (SPI/AOI/X-ray/ICT)
1–2 | Minor / cosmetic | Unlikely | Detected at design review / by data
OVERRIDE RULES (an average must never dilute a release blocker)
• Any finding scored 5 (unknown critical characteristic) OPEN → no fabrication or production release.
• Any pre-build High (score 4) OPEN → prototype fabrication release blocked until closed.
• Any supplier-dependent High → requires WRITTEN fabricator/CM acceptance, not internal judgement.
• Unknown critical characteristic (finish, via-in-pad, MSL) → scored as open risk, not a neutral 3.
• Scorecard average is informational ONLY; the gate decision is driven by open High/Critical findings.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S14] DFM/DFA reviews
Standards: IPC-A-610
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 4. Source Manifest
Source-Data Manifest (evidence baseline)
Every quantitative finding cites one of these artifacts from the design's own released package (baseline rev ACB_0001_2). A content fingerprint fixes the exact object; internal storage locations are omitted by design.
# | Artifact (the board's own released data) | Baseline | Fingerprint
1 | Released BOM (mfr/MPN/package/price) | rev ACB_0001_2 | 11d508a117
2 | NC-drill — plated (Excellon tool table) | rev ACB_0001_2 | a473e9bd24
3 | NC-drill — non-plated | rev ACB_0001_2 | ec887e56de
4 | Field-solver stack-up / material model | rev ACB_0001_2 | 49a35ce89b
5 | Placement list (X/Y/side/mount) | rev ACB_0001_2 | 1c0c00196e
6 | ODB++ CAD netlist (IPC-D-356 equivalent) | rev ACB_0001_2 | d8913714b9
7 | ODB++ eda/data (net records) | rev ACB_0001_2 | 63e1079db4
8 | Solder-paste artwork — TOP | rev ACB_0001_2 | 9b2526d01c
9 | Solder-paste artwork — BOTTOM | rev ACB_0001_2 | e8ab351c30
10 | Copper artwork set — 10 layers | rev ACB_0001_2 | (10 files)
11 | Native board record (layer stack) | rev ACB_0001_2 | (binary)
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: the complete released design package at baseline rev ACB_0001_2 — BOM, NC-drill (plated + non-plated), stack-up/material model, placement list, ODB++ netlist and net records, solder-paste and copper artwork, native board records (items 1–12 above).
Standards: IPC-9252 / IPC-D-356 (netlist and test-access data model used to interpret items 6–7); per-finding standards are listed on '0. References & Citations'.
Internal storage locations are omitted by design; artifacts are identified by content fingerprint only.

## 5. Technical Baseline
Product & PCB Technical Baseline (from source data)
Verified facts with source + object/coordinate. 'NOT-IN-DATA' = genuinely absent after exhaustive search (see Stack-up & BOM sheets).
Attribute | Value (from data) | Source object / location | Fact / Assumption
Board outline | ≈ 289.6 × 148.7 mm | Drill extents, ThruHolePlated.ncd (min/max X,Y) | Fact (drill span)
Copper layers | 10 (Top + 8 internal + Bottom) | Gerber 1-Top … 10-Bottom | Fact
Assembly type | Double-sided SMT | Paste M-SolderPasteTop + N-SolderPasteBot present | Fact
Placements (instances) | 2,191 (680 top / 1,511 bottom) | ComponentList.csv Side column | Fact
Placements (BOM qty) | 2,047 across 268 BOM lines | BOM ODS sum(QTY) | Fact
Mount split | SMD 2,147 · Through 24 · Mixed 5 | ComponentList.csv Mount Type | Fact
Main CPU | U1 NXP T2080, PBGA896, 0.8 mm pitch, 25×25 mm | ComponentList cell PBGA896-0_8MM-25X25-FAN | Fact
Other bottom-term. arrays | U50 LGA-196 (15×15), U76 LGA-133 (15×15) | ComponentList cell LGA-196/133-15X15 | Fact
Largest connectors | J18 MXM3.0 316-pin 0.5 mm; J3F1/2 DDR3 DIMM 204/206-pin; J19 HDMI SMD | BOM + ComponentList | Fact
Total holes | ≈ 4,768 (4,737 plated + 31 non-plated/contour) | NCDrill tool counts (see Drill sheet) | Fact
Min plated drill | 0.20 mm (tool T10 × 4,533) | ThruHolePlated.ncd tool table | Fact
Via technology | Through-vias only (no blind/buried/microvia) | Single ThruHole drill set; no span files | Fact
Named nets | 1,691 (1,692 dict − $NONE$) | eda/data NET records | Fact
Power/ground nets | 107 | eda/data classification | Fact (keyword)
Nets with copper access | 1,482 (209 nets have NO access feature) | cadnet netlist access records | Fact
Access features | 9,187 = 4,629 vias + 4,558 pads | cadnet netlist type field | Fact
Dedicated test points | 108 (TP14–TP133) = 6.4% of named nets | Schematic testpoint symbols | Fact
Material (field-solve) | FR-4; Er 4.4 & 4.7; Cu 0.5 oz + 1 oz | layer.fsc dielectric/copper values | Fact (template)
Board thickness | 1.6 mm | KiCad general(thickness 1.6) | Fact
Ordered fab stack-up | NOT-IN-DATA (no released build order/Tg/CAF/finish) | Exhaustive search — evidence memo | Fact (absent)
Surface finish | NOT-IN-DATA (no ENIG/OSP call-out) | Exhaustive search — evidence memo | Fact (absent)
Impedance targets | NOT-IN-DATA (field-solved only; no target Ω/tol) | layer.fsc L/C matrices; no fab table | Fact (absent)
Component MSL | NOT-IN-DATA (no BOM MSL column) | BOM ODS header | Fact (absent)
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S2] NC drill — plated (tool table) · [S3] NC drill — non-plated · [S4] Field-solver stack-up/material · [S5] Placement list (X/Y/side/mount) · [S6] ODB++ CAD netlist (access pts) · [S7] ODB++ eda/data (net records) · [S10] Copper Gerber set 1-Top…10-Bottom · [S11] Altium board record (LayerStack) · [S12] KiCad board (thickness) · [S13] Evidence-recovery memo (OCR)
Standards: IPC-2226
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 6. Drill & Via
Drill & Via Analysis (from Excellon tool tables)
Source: NCDrill/*.ncd, board Mas100n3 ACB_0001_2, format 3.3/MM/leading. Aspect ratio at 1.6 mm board thickness.
Tool | Ø drill (mm) | Qty | Type | Aspect @1.6mm (drill) | Aspect @finished (−0.05) | Note
T10 | 0.20 | 4533 | Plated via/PTH | 8.0:1 | 10.7:1 | 95% of all holes — worst-case aspect ratio; fab plating-reliability sign-off required (IPC-6012)
T12 | 0.25 | 18 | Plated | 6.4:1 | 8.0:1
T11 | 0.30 | 77 | Plated | 5.3:1 | 6.4:1
T13 | 0.40 | 1 | Plated | 4.0:1 | 4.6:1
T07 | 0.60 | 23 | Plated | 2.7:1 | 2.9:1
T02 | 0.70 | 18 | Plated | 2.3:1 | 2.5:1
T01 | 0.80 | 3 | Plated | 2.0:1 | 2.1:1
T04 | 1.00 | 46 | Plated | 1.6:1 | 1.7:1
T09 | 1.40 | 1 | Plated | 1.1:1 | 1.2:1
T17 | 2.40 | 11 | Plated PTH | 0.7:1 | 0.7:1 | mounting/tooling
T18 | 3.20 | 2 | Plated | 0.5:1 | 0.5:1 | mounting/tooling
T16 | 4.10 | 4 | Plated (mtg) | 0.4:1 | 0.4:1 | mounting/tooling
T06 | 1.10 | 6 | Non-plated | 1.5:1 | 1.5:1
T05 | 1.60 | 6 | Non-plated | 1.0:1 | 1.0:1
T14 | 2.00 | 3 | Non-plated | 0.8:1 | 0.8:1
T15 | 2.30 | 1 | Non-plated | 0.7:1 | 0.7:1
Worst case: 0.20 mm plated via at 1.6 mm = 8.0:1 (drill) ≈ 10.7:1 (finished, 25 µm plating each wall). This is the governing fab-capability & hole-wall reliability check (IPC-6012). Confirm fab aspect-ratio limit, via-fill/plug status, and via-in-pad treatment under U1.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S2] NC drill — plated (tool table) · [S3] NC drill — non-plated · [S12] KiCad board (thickness)
Standards: IPC-6012 · IPC-4761 · IPC-2221
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 7. Net & Test Reconciliation
Net & Test-Coverage Reconciliation
Resolves the 1,691 vs 1,482 discrepancy. Access-point count ≠ test coverage. Probe SIDE is not encoded in the netlist.
Quantity | Count | % of named nets | Source / method
Net dictionary entries | 1692 |  | cadnet $N + eda/data NET
Named nets (− $NONE$) | 1691 | 100.0% | 1692 − 1
Power / ground nets | 107 | 6.3% | keyword classification (GND/VCC/Vx…)
Signal nets (eligible) | 1584 | 93.7% | 1691 − 107
Nets WITH ≥1 copper access | 1482 | 87.6% | cadnet distinct access nets
Nets with NO access feature | 209 | 12.4% | 1691 − 1482 (no-probe candidates)
Total access features | 9187 |  | cadnet records
— via access features | 4629 |  | type 'v'
— pad access features | 4558 |  | type '0'
Dedicated test points (TP14–TP133) | 108 | 6.4% | schematic testpoint symbols
Bottom-side single-side ICT access | NOT DET. | — | probe SIDE not encoded (all 'T') → DFT tool required
Do NOT equate 9,187 access points with test coverage. Real ICT node coverage depends on bottom-side single-side access, via tenting and probe pitch — none of which are in this data. A DFT access analysis on the soldermask + pad geometry is required to state fault coverage. Dedicated-TP coverage is only 6.4% of named nets; boundary-scan (JTAG/COP, likely header J3) is needed for BGA nets ICT cannot reach.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S6] ODB++ CAD netlist (access pts) · [S7] ODB++ eda/data (net records)
Standards: IPC-9252/D-356
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 8. Stackup & Impedance
Stack-up & Controlled-Impedance Status
What exists in the CAD vs what a fab package needs. Dk conflict is flagged, not silently resolved.
Item | Status | Evidence | Still required for fabrication
Copper layer count | Verified | Gerber 1-Top…10-Bottom (10) | —
Copper weights | Present | layer.fsc: 17.78 µm (0.5 oz) + 35.56 µm (1 oz) | Per-layer assignment on the fab stack drawing
Dielectric material | Present (generic) | layer.fsc FR-4; Er 4.4 & 4.7 | Exact laminate family, glass style, resin content
Dielectric constant | CONFLICT | Altium signal Dk 3.7 vs layer.fsc Er 4.4–4.7 vs Altium default 4.8 | Fab must state controlling laminate Dk + test method/freq
Ordered build (core/prepreg) | NOT-IN-DATA | No released stack drawing | Ordered layer build, core/prepreg split, symmetry
Finished thickness / tol | 1.6 mm (KiCad) — no ±tol | general(thickness 1.6) | Finished thickness ± tolerance reconciliation
Tg / Td / Z-CTE / CAF | NOT-IN-DATA | — | Material thermal/reliability grade for lead-free reflow
Surface finish | NOT-IN-DATA | exhaustive search | Select via trade study; fab + CM approval
Impedance geometry | Field-solved | layer.fsc L/C matrices, trace/dielectric geometry | Formatted impedance TABLE (target Ω + tol per class)
Impedance targets/coupon | NOT-IN-DATA | no net-class targets in CAD | Target Z0, tolerance, controlled layers, TDR coupon plan
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S4] Field-solver stack-up/material · [S11] Altium board record (LayerStack) · [S12] KiCad board (thickness) · [S13] Evidence-recovery memo (OCR)
Standards: IPC-2221 · IPC-6012 · IPC-A-600
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 9. BOM MSL AML
BOM, MSL & AML Review (line-level)
Source: PORTATILE_1_1_BOM_NEW_DEF.ods (268 lines, 2,047 placements). 'Mfr + MPN present' ≠ approved AML.
Metric | Value | Interpretation / gap
BOM lines | 268 | —
Total placements (Σqty) | 2047 | matches ComponentList instance count band
Unique manufacturers | 91 | broad supply base
Lines missing MPN | 3 | BOM incomplete — resolve before quote
Lines missing manufacturer | 2 | single-source ambiguity
Distinct package strings | 113 | footprint NAMING not standardized (SOT-23/SOT_23/SOT23; SMD_xxxx) → library-control finding
MSL column | ABSENT | no per-part MSL → J-STD-033 handling cannot be planned
Alternate/2nd-source column | ABSENT | single-source AML only; no approval status / do-not-substitute
Lifecycle / PCN / counterfeit | ABSENT | no lifecycle or risk data in BOM
KEY DEVICES (from BOM/ComponentList)
Ref | Description | Package | Mfr | MPN
U1 | QorIQ T2080 MPU DDR3/3L quad-e6500 | PBGA896 | NXP | T2080NXN8PTB
U50 | PCIe 2.0 6-port/6-lane switch | LGA-196 | DIODES | PI7C9X2G612GP
U38 | Gigabit Ethernet transceiver | QFN48 | MICREL | KSZ9031RNXCA
J18 | MXM 3.0 GPU card-edge connector | 324-pin 0.5 mm | JAE | MM70-314-310B1-2-R
J3F1/J3F2 | DDR3 SO-DIMM socket | 204-pin | TE | 2013022-1 / 2-2013310-1
J19 | HDMI Type-A receptacle (SMD) | 19-pin SMD | TE | 2041481-1
CN1,CN2 | USB 3.0 Type-A (THT) | 9-pos TH | Molex | 483950003
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S5] Placement list (X/Y/side/mount)
Standards: J-STD-033 · IPC-7351
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 10. BGA & Package
BGA / LGA / QFN Package Assessment
Package data taken from the released BOM and CAD. U1 PBGA and U50/U76 LGA are all bottom-terminated, X-ray-critical packages.
Ref | Package | Pitch / size | Balls/pads | Escape / inspection status | Confirmation required
U1 | PBGA896 | 0.8 mm / 25×25 mm | 896 | Through-via escape on 10 layers; via-in-pad status NOT in data | Via location vs land; tented/plugged/filled/capped; X-ray criteria; warpage/HIP; rework envelope
U50 | LGA-196 | 0.8 mm / 15×15 mm | 196 | Bottom-terminated; hidden joints → X-ray | Pad/paste def; void limit; X-ray sampling
U76 | LGA-133 | — / 15×15 mm | 133 | Bottom-terminated; hidden joints → X-ray | Confirm pitch; X-ray plan
QFN/DFN/SON (17) | QFN/DFN | various | — | Thermal-pad voiding; windowpane paste (IPC-7093) | Per-part thermal-pad paste %, X-ray/endoscope
CORRECTION vs earlier screening: T2080 is 0.8 mm pitch (cell PBGA896-0_8MM-25X25-FAN), NOT '0.5 mm-pitch class'. 0.8 mm pitch eases escape/inspection but the through-via-only escape + via-in-pad question and warpage on a thin cut-out board remain the governing risks. A dedicated quantitative BGA escape study (route count/channel, layer transitions, copper balance, warpage) is still required.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S5] Placement list (X/Y/side/mount) · [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S6] ODB++ CAD netlist (access pts)
Standards: IPC-7095 · IPC-7093 · IPC-A-610 · IPC-4761
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 11. Risk Register
Quantitative Risk Register (severity-first, traceable)
S/O/D 1–10, Action Priority per Rubric sheet. Each row cites source file + object/location. Fact vs Assumption stated. Residual = risk after the recommended action.
ID | Discipline | Finding (observed condition) | S | O | D | AP | Source file | Object / location | Method | Conf. | Fact/Assump | Gate effect | Recommended action | Residual | Owner | Status
DFM-01 | PCB-fab DFM | No released fab-doc package: no fab drawing, ordered stack-up, impedance table, IPC class, finished-thickness tol, or IPC class. CAD has material/impedance engineering only. | 9 | 7 | 8 | High | layer.fsc; Altium PcbDoc | board record; no fab drawing | field/strings | High | Fact (absent) | Blocks fab/quote | Produce fab-doc package; export ordered stack-up + impedance table; state class/thickness/Tg/CAF; fab sign-off | Med — after fab review | PCB eng | Open
DFM-02 | PCB-fab DFM | Through-via-only 0.20 mm min drill on 1.6 mm board = 8.0:1 (drill) ≈10.7:1 (finished) worst-case aspect ratio; 4,533 such vias (95% of holes). | 7 | 6 | 6 | High | ThruHolePlated.ncd | tool T10 Ø0.20 ×4533 | Excellon parse | High | Fact | Blocks fab | Fab sign-off of aspect ratio & hole-wall reliability (IPC-6012); confirm plating throw | Med | PCB eng + fab | Open
DFM-03 | PCB-fab DFM | U1 PBGA896 (0.8 mm, 25×25) escaped with through vias; via-in-pad treatment (tented/plugged/filled/capped) NOT in data. Via-in-pad ≠ automatic — confirmation required. | 8 | 5 | 7 | High | ComponentList; netlist | U1 cell PBGA896-0_8MM; via features | cell/geom | Medium | Assumption—confirm | Blocks fab | Confirm via location vs land + fill/planarize (IPC-4761); fab yield history; X-ray criteria | Med | PCB eng + fab | Open
DFM-05 | PCB-fab DFM | PCB surface finish NOT specified for a 896-ball BGA + 0201. Do NOT default to ENIG; select by trade study. | 8 | 6 | 5 | High | exhaustive search | no finish call-out | search | High | Fact (absent) | Blocks quote | Surface-finish trade study (planarity/solderability/reflow cycles/cost); fab+CM approval | Low—after study | PCB eng | Open
DFM-06 | PCB-fab DFM | No real panel/depanel drawing (prior CCI/dima DXFs are donor-board PHOTOS, OCR-verified). Large 290×149 board with cut-outs → warpage/depanel stress. | 6 | 6 | 5 | High | OCR of DXF rasters | dima/CCI = images | OCR | High | Fact (absent) | Blocks fab | Panel drawing: rails, fiducials, coupons, tabs/V-score away from BGA/MLCC, support under cut-outs | Med | PCB+CM | Open
DFM-08 | PCB-fab DFM | Material grade generic (FR-4); Dk conflict (3.7 vs 4.4–4.7 vs 4.8); no Tg/Td/CAF for lead-free reflow. | 5 | 5 | 5 | Medium | layer.fsc; Altium | Er 4.4/4.7; Dk 3.7 | field/strings | High | Fact | Conditional | State laminate family + Tg/Td/CAF; resolve Dk with fab; confirm availability at ≥2 fabs | Low | PCB eng | Open
PROC-04 | PCBA DFM | 0201 (159×) + large connector pads + potential via-in-pad on ONE stencil → area-ratio conflict. Step-stencil NOT yet justified by calculation. | 6 | 6 | 5 | High | Paste M/N Gerber; BOM | 0201 apertures | gerber | Medium | Fact/analysis-needed | Blocks proto | Compute aperture area ratios (IPC-7525 ≥0.66); size step-stencil only if conflict proven; windowpane BGA/QFN | Low | CM/SMT | Open
PROC-06 | PCBA DFM | MSL handling undefined (no BOM MSL). T2080 BGA/LGA/QFN need bake-and-bag (J-STD-033) or popcorn/delam risk. | 8 | 5 | 6 | High | BOM ODS | no MSL column | header | High | Fact (absent) | Blocks proto | Per-part MSL from datasheets; floor-life/bake per J-STD-033 (not J-STD-020 as bake) | Low | CM+component | Open
PROC-07 | PCBA DFM | Bottom-side-heavy build: 1,511 of 2,191 placements on BOTTOM. Bottom parts see 2nd reflow → retention/adhesive + double-sided profile risk. | 6 | 5 | 5 | High | ComponentList.csv | Side=bottom ×1511 | csv | High | Fact | Conditional | Double-sided reflow profile; bottom-side mass/adhesive check; AOI both sides | Low | CM/SMT | Open
PROC-09 | PCBA DFM | Footprint library not standardized: 113 distinct package strings incl. duplicate names (SOT-23/SOT_23/SOT23). Footprints not verified vs component drawings. | 4 | 5 | 6 | Medium | BOM ODS | package column | parse | High | Fact | Conditional | Independent footprint validation vs mfr land patterns (IPC-7351); dedupe library | Low | PCB eng | Open
DFA-01 | DFA | No panelization / assembly-DFM package; no assembly sequence, fixture or takt defined. | 6 | 6 | 5 | High | package (absent) | — | review | High | Fact (absent) | Blocks proto | Author assembly flow + panel + fixtures (see Assembly Flow sheet) | Med | ME/CM | Open
DFA-02 | DFA | Thermal-module clamp lands on U1 BGA; spring-screw sequence/torque undefined → board flex / solder-joint damage. | 9 | 5 | 7 | High | mech review; BOM | thermal module + U1 | review | Medium | Assumption—analyze | Blocks proto | Captive screws, marked sequence, torque, strain-gauge board-flex validation (see Thermal sheet) | Med | ME | Open
DFA-03 | DFA | BGA/QFN process controls (X-ray, SPI, MSL) not evidenced for U1 + U50/U76 LGA + 17 QFN. | 8 | 5 | 7 | High | process data (absent) | U1/U50/U76/QFN | review | High | Fact (absent) | Blocks proto | Define X-ray criteria + SPI + MSL controls (see Inspection Plan) | Low | CM/quality | Open
DFA-06 | DFA | Customer ports (HDMI J19 SMD, DC-in, USB/RJ45) may react mating force through solder — load path not analysed. | 7 | 5 | 6 | High | BOM; mech | J19 SMD etc. | review | Medium | Assumption—analyze | Blocks proto | Connector load-path analysis + enclosure support (see Connector sheet). IPC-A-610 is acceptance, not structural basis | Med | ME | Open
DFT-01 | DFT | Real ICT node coverage unknown: probe SIDE not encoded; only 6.4% dedicated-TP coverage; 209 no-access nets. | 7 | 6 | 7 | High | cadnet netlist | access records | parse | High | Fact | Blocks pilot | DFT bottom-side access study for fault coverage; +boundary-scan (J3 JTAG) (see DFT sheet) | Med | test eng | Open
DOC-01 | Doc control | Schematic/PCB/BOM/fab-data revisions not reconciled to one released baseline; ECAD↔BOM↔P&P not cross-checked. | 5 | 5 | 6 | Medium | multiple | rev fields | review | Medium | Fact | Conditional | ECAD/BOM/P&P reconciliation; fix baseline revisions (see Doc Control) | Low | PLM | Open
BLD-01 | Validation | No pilot-build evidence: no yield, defect pareto, or process-capability data exists. | 7 | 7 | 6 | High | — (absent) | — | review | High | Fact (absent) | Blocks pilot/vol | Run EVT/DVT pilot with KPI capture (see Pilot Plan) before any volume decision | Med | NPI | Open
Action Priority counts: |  | 14 High / 3 Medium / 0 Low
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S2] NC drill — plated (tool table) · [S4] Field-solver stack-up/material · [S5] Placement list (X/Y/side/mount) · [S6] ODB++ CAD netlist (access pts) · [S13] Evidence-recovery memo (OCR) · [S14] DFM/DFA reviews
Standards: IPC-6012 · IPC-7095 · IPC-4761 · IPC-7525 · IPC-7093 · IPC-A-610 · J-STD-001 · J-STD-033 · JEDEC J-STD-020 · IPC-7711/7721
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 12. DFM Scorecard
DFM Scorecard (with criteria & evidence)
Score = readiness/risk (1 solid … 5 not-ready). Criterion + supporting evidence stated. Average is informational; open High/Critical findings govern the gate (see Rubric).
Category | Score | Defined criterion for the score | Supporting evidence / finding | Gate min
Supplier-capability alignment | 4 | Advanced-but-standard; no fab sign-off yet | 10L, 0.20mm drill, 8:1 AR — DFM-01/02 | ≤3
Material availability | 3 | Generic FR-4; grade/availability unconfirmed | DFM-08; layer.fsc | ≤3
Stack-up release | 4 | Engineered but no released fab stack drawing | DFM-01; Stackup sheet | ≤3
Controlled impedance release | 3 | Field-solved; no fab table/coupon | DFM-01; layer.fsc | ≤3
Via technology | 4 | 8:1 drill AR, via-in-pad unconfirmed | DFM-02/03; Drill sheet | ≤3
BGA escape | 3 | 0.8mm pitch eases escape; through-via only | DFM-03; BGA sheet | ≤3
Surface finish | 5 | Unknown critical characteristic — open risk | DFM-05 (absent) | ≤3
Panelization | 4 | No real panel drawing | DFM-06 (absent) | ≤3
Copper balance / warpage | 4 | Thin cut-out board; not analysed | PROC-07; not run | ≤3
Footprint quality | 3 | Not validated; library not standardized | PROC-09 | ≤3
Paste printing | 4 | 0201+large pads; step-stencil unproven | PROC-04 | ≤3
Reflow / MSL | 4 | MSL undefined; double-sided profile | PROC-06/07 | ≤3
Testability (fab) | 3 | Netlist supports flying-probe | Net sheet | ≤3
Cost / yield model | 4 | No yield model; many risk drivers | BLD-01 | ≤3
Average (informational) | 3.7 | 9 categories at High (≥4) — these, not the average, drive the gate.
Surface finish scored 5 (unknown critical characteristic) → per override rules, no fabrication/production release until closed. DFM is NOT approvable at this maturity.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S2] NC drill — plated (tool table) · [S4] Field-solver stack-up/material · [S5] Placement list (X/Y/side/mount) · [S6] ODB++ CAD netlist (access pts)
Standards: IPC-6012 · IPC-7095 · IPC-4761 · IPC-7525 · IPC-7351 · IPC-2152
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 13. DFA Scorecard
DFA Scorecard (with criteria & evidence)
Score = readiness/risk (1 solid … 5 not-ready). Criterion + supporting evidence stated. Average is informational; open High/Critical findings govern the gate (see Rubric).
Category | Score | Defined criterion for the score | Supporting evidence / finding | Gate min
Part-count efficiency | 3 | 2,047 placements, modular; not optimised-analysed | DFA op sheet | ≤3
Process standardization | 3 | 0402 dominant; ≥16 pkg types; 0201 | BOM packages | ≤3
SMT compatibility | 3 | Standard SMT front-end | ComponentList | ≤3
Manual-operation content | 4 | Modules+12 cables+thermal module; high manual | DFA-01 | ≤3
Error-proofing | 4 | Thermal-module sequence/torque undefined | DFA-02 | ≤3
Tool accessibility | 3 | Dense double-sided; access not verified | review | ≤3
Connector accessibility | 3 | Tall connectors; load path unverified | DFA-06 | ≤3
Fastener complexity | 3 | No fastener schedule yet (was optimistic 2) | Fastener sheet | ≤3
Inspection coverage | 4 | X-ray/SPI plan not defined | DFA-03 | ≤3
Test access | 4 | ICT node coverage unknown | DFT-01 | ≤3
Reworkability | 4 | 896-ball BGA rework specialist-only | IPC-7711/21 | ≤3
Automation readiness | 3 | Manual back-end | review | ≤3
Ergonomics | 3 | Not analysed per-operation (was 2, unsupported) | Ergonomics-TBD | ≤3
Tolerance robustness | 4 | No stacks run | Tolerance sheet | ≤3
Final-system integration | 4 | Port/heat-sink stacks unverified | DFA-06 | ≤3
Thermal-assembly robustness | 4 | Clamp on BGA; unvalidated | DFA-02 | ≤3
Average (informational) | 3.5 | 8 categories at High (≥4) — these, not the average, drive the gate.
Multiple pre-build High categories open (thermal-module error-proofing, BGA process, test access). DFA disposition is CONDITIONAL prototype only — not approved.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S5] Placement list (X/Y/side/mount) · [S6] ODB++ CAD netlist (access pts)
Standards: IPC-A-610 · IPC-7095 · IPC-7093 · IPC-7711/7721
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 14. Inspection Plan
Inspection & Control Plan
Expanded from a 6-line matrix. 'Mandatory X-ray' is risk-based, not a casual standard citation. Acceptance criteria and sampling to be fixed with CM.
Feature | Defect | Process stage | Method | Coverage (proposed) | Acceptance criterion | MSA | Reaction plan | Record
Paste volume (0201) | Insufficient/excess | Post-print | SPI | 100% | IPC-7525 area-ratio ≥0.66; volume 70–130% target | Gage R&R req. | Stop/clean stencil; re-print | SPI log
0201 placement | Tombstone/shift | Post-place | AOI | 100% | IPC-A-610 Cl.2 (target) | req. | Feeder/nozzle check | AOI log
U1 BGA joints | Open/HIP/bridge/void | Post-reflow | X-ray | Sampling→100% (risk-based) | IPC-7095 void <25%; no HIP | req. | Quarantine; profile review | X-ray images
U50/U76 LGA + 17 QFN | Thermal-pad void | Post-reflow | X-ray/endoscope | Sampling | IPC-7093 void limit TBD | req. | Paste % adjust | X-ray
Polarity/presence | Wrong/missing | Post-place | AOI | 100% | Correct per BOM/P&P | — | Rework | AOI
THT fill (24 THT) | Insufficient fill | Post-solder | AOI/X-ray/manual | 100% of THT | J-STD-001 fill class | — | Hand-touch | record
Connector coplanarity | Lifted lead | Post-reflow | AOI | 100% | IPC-A-610 | — | Rework | AOI
Board warpage | Bow/twist | Bare + post-reflow | Gauge | Sample | IPC-6012 ≤0.75% | req. | Fab CA | measurement
Cleanliness | Ionic residue | Post-clean | ROSE/IC | Sample | IPC J-STD-001 | — | Re-clean | report
Programming | Fail/verify | Post-assy | In-system | 100% | Verify pass | — | Re-program | log
ICT/boundary scan | Structural fault | Test | ICT+JTAG | Per DFT study | Coverage target TBD | — | Diagnose | test log
Functional test | System fail | Test | FT fixture | 100% | FT spec (TBD) | — | Repair loop | FT log
Coverage %, sampling and acceptance limits are PROPOSED and must be set with the CM against process capability. X-ray extent for U1 is risk-based, justified by hidden-joint inaccessibility (IPC-7095), not by blanket 'mandatory'.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S5] Placement list (X/Y/side/mount) · [S8] Solder paste — TOP Gerber · [S9] Solder paste — BOTTOM Gerber
Standards: IPC-7525 · IPC-A-610 · IPC-7095 · IPC-7093 · J-STD-001 · IPC-6012
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 15. DFT Coverage
DFT & Test-Coverage Analysis
Fault coverage is NOT established by access-point count. Values below are the measured access data; coverage % requires a DFT tool run.
Metric | Value / status | Basis / action
Named nets | 1691 | eda/data
Signal (eligible) nets | 1584 | 1691 − 107 power/gnd
Nets with copper access | 1482 | cadnet
No-access nets | 209 | no probe candidate — investigate
Access features | 9187 | 4,629 via + 4,558 pad
Dedicated test points | 108 | 6.4% of named nets
Bottom-side single-side access | NOT DETERMINED | probe side not encoded → run DFT tool on mask+pad geometry
Via-tenting status | UNKNOWN | tented via not probeable — extract from mask
Structural fault coverage % | TBD | DFT/ICT tool output required
Boundary-scan coverage | TBD | JTAG/COP via header J3 for BGA nets
Recommended test sequence | 1 unpowered-shorts → 2 current-limited power-up → 3 rail validation → 4 program/recover → 5 ICT+boundary-scan → 6 memory/storage → 7 interface → 8 thermal/fan → 9 system FT | define + fixture
Action DFT-01: quantify real node coverage before the expensive thermal/chassis integration; do not proceed to pilot on access-point count alone.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S6] ODB++ CAD netlist (access pts) · [S7] ODB++ eda/data (net records)
Standards: IPC-9252/D-356
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 16. Assembly Flow
Assembly Process Flow & DFA Operation Analysis
Numbered sequence with per-step data. Cycle times are placeholders to be measured at pilot. This flow does NOT exist in the supplied data (DFA-01).
# | Operation | Tool/fixture | Force/torque | Access/risk | Verification | Rework path
1 | MSL bake & bag (per J-STD-033) | Oven/dry cabinet | — | Popcorn if skipped | Floor-life log | Re-bake
2 | Bottom paste → SPI → place → reflow | Printer/SPI/P&P/oven | — | 1,511 bottom parts; area-ratio | SPI+AOI | Reprint/replace
3 | Top paste → SPI → place (incl. U1 BGA) → reflow | same | — | BGA warpage/HIP; 2nd reflow | SPI+AOI+X-ray | BGA rework (specialist)
4 | X-ray U1/U50/U76/QFN | X-ray | — | Hidden joints | X-ray criteria | Rework
5 | THT insert (DC jack, USB, JST, headers) | Selective/hand | insertion | 24 THT; access on dense board | AOI/manual | Hand-touch
6 | Clean + program (NOR/SPI) | Cleaner/programmer | — | — | Verify | Re-program
7 | ICT + boundary scan | Fixture/JTAG | probe | Bottom access unknown | Coverage report | Diagnose
8 | Functional test | FT fixture | — | — | FT pass | Repair
9 | Thermal-module assembly (TIM+heat-sink) | Torque driver/fixture | spring-screw torque (TBD) | Clamp on U1 BGA — DFA-02 | Strain-gauge+thermal | Re-TIM rule
10 | Module insertion (SO-DIMM/MXM/3×M.2) | Hand | insertion | retention screws | Presence | Reseat
11 | Chassis integration + 12 cables | Hand/torque | screw torque | Port alignment; cable pinch | Inspection | Rework
12 | System functional test | System bench | — | — | System pass | Repair/replace
Every step needs measured cycle time, operator access, error mode and defined verification before pilot. Part/operation counts: 2,047 placements, 24 THT, ≥5 module insertions, 12 cables, 1 thermal module, ≥1 board flip (double-sided).
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S5] Placement list (X/Y/side/mount) · [S8] Solder paste — TOP Gerber · [S9] Solder paste — BOTTOM Gerber
Standards: IPC-7095 · IPC-A-610 · IPC-7711/7721 · J-STD-033
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 17. Mech Analyses (open)
Fastener · Connector · Thermal · Tolerance · Board-Strain (analysis register)
These quantitative analyses are NOT yet performed. Each row states the required study and its based onputs; the affected scores remain open until the studies exist.
Analysis | Based onputs | What must be produced | Status
Fastener schedule | Chassis M3 + 18 heat-set inserts; thermal-module spring screws | Qty/length/dia/head/drive/torque±tol/captive/coating/grounding/feed/access/sequence | Not run
Connector load-path | J19 HDMI SMD; DC-in; USB/RJ45 on IO board | Mating/unmating/user force; retention; PCB attach; enclosure support; load path; cycles; test | Not run (DFA-06)
Thermal-module clamp | U1 PBGA896; MXM; 2 fans; TIM; spring screws | TIM thickness/compression; screw rate/torque/sequence; package clamp load; board deflection; allowable strain; gauge locations; re-TIM rule | Not run (DFA-02)
Tolerance stacks | 290×149 board; ports; standoffs; heat-sink | Ports-to-openings; holes-to-standoffs; CPU-to-heatsink; TIM compression; ground-spring; connector alignment; cable reach — nominal + WC/stat + margin | Not run
Board-strain map | U1 BGA; U50/U76 LGA; large MLCC; cut-out necks | Strain-risk map for connector insert, screw, clamp, probe, install, depanel, rework — with strain-gauge validation plan | Not run
Copper balance/warpage | 10 layers; large planes; cut-outs | Cu % per layer; top/bottom & quadrant imbalance; predicted + measured bow/twist ≤0.75% | Not run
None of these can be closed by documentation alone — some may drive layout or mechanical redesign.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S5] Placement list (X/Y/side/mount) · [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S13] Evidence-recovery memo (OCR)
Standards: IPC-A-610 · IPC-6012
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 18. Panelization
Panelization & Depanelization Requirements
Board 290×149 mm with battery/fan/connector cut-outs. No real panel drawing exists (DFM-06). This defines the required panel concept — route to fab/CM.
Parameter | Requirement / recommendation
Panel size / boards-per-panel | Set with fab to material utilization; likely 1-up given board size
Rails / tooling holes | Rails ≥10 mm; tooling holes + global fiducials on rails
Fiducials | Global (panel) + local (U1 BGA, fine-pitch) fiducials
Coupons | Impedance TDR coupon + microsection coupon per panel
Tab / V-score strategy | Tabs/perforation AWAY from U1 BGA & MLCC; no V-score across cut-out necks
Board support | Support under battery/fan cut-outs for 0201 print + connector insertion
Depanel method | Router (not V-score) near stress-sensitive parts; keep-outs defined
Stress-sensitive keep-outs | U1, U50/U76, large MLCC, edge connectors
Traceability | Serialization/barcode surviving depanel
Responsibility: produce with the fabricator/CM before fabrication. This is a pre-build blocker.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S2] NC drill — plated (tool table) · [S10] Copper Gerber set 1-Top…10-Bottom · [S13] Evidence-recovery memo (OCR)
Standards: IPC-A-600 · IPC-6012
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 19. Pilot Plan & KPIs
Prototype / Pilot Validation Plan & Manufacturing KPIs
No build data exists (BLD-01). No production recommendation until these KPIs are measured or explicitly stated pending.
Element | Definition / target
Phase | EVT → DVT → PVT (or equivalent)
Quantity | EVT ≥5; DVT ≥20; PVT per plan
Build location / process | Chosen CM, intended production line
Data to collect | Yields per stage, defect pareto, rework min/board, scrap, cycle time
Stop-build criteria | Any safety defect; BGA open rate > target; first-pass yield < floor
Gate closure | Defect pareto reviewed; capability targets met; sign-off meeting
MANUFACTURING KPIs (capture at pilot)
KPI | Target (to set) | Status
PCB fabrication yield | TBD | Pending
Paste-print yield (SPI) | TBD | Pending
Placement defect rate (ppm) | TBD | Pending
AOI first-pass yield | TBD | Pending
X-ray defect rate (BGA) | TBD | Pending
PCBA first-pass yield | TBD | Pending
ICT yield | TBD | Pending
Functional-test yield | TBD | Pending
Rolled throughput yield | TBD | Pending
Rework minutes/board | TBD | Pending
Scrap cost/board | TBD | Pending
Top defect modes | TBD | Pending
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S14] DFM/DFA reviews
Standards: IPC-A-610 · J-STD-001
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 20. Closure Tracker
Action & Closure Tracker
One exact closure gate per action. Owners, dates, verification and residual risk required for disciplined execution.
Action ID | Linked finding | Required action / deliverable | Accountable owner | Supplier owner | Opened | Due | Closure gate | Blocker? | Verification method | Closure evidence | Residual | Status
A-01 | DFM-01 | Release fab-doc package (drawing+stack-up+impedance table+class) | PCB eng | PCB fab | TBD | TBD | Pre-fab | YES | Fab DFM report | — | Med | Open
A-02 | DFM-02/03 | Fab sign-off aspect ratio + BGA via-in-pad fill/planarize | PCB eng | PCB fab | TBD | TBD | Pre-fab | YES | Written fab acceptance | — | Med | Open
A-03 | DFM-05 | Surface-finish trade study + fab/CM approval | PCB eng | fab+CM | TBD | TBD | Pre-quote | YES | Trade-study doc + approval | — | Low | Open
A-04 | DFM-06/18 | Panel & depanel drawing | PCB eng | CM | TBD | TBD | Pre-fab | YES | Panel drawing released | — | Med | Open
A-05 | PROC-04 | Stencil area-ratio calc + step-stencil decision | SMT eng | CM | TBD | TBD | Pre-proto | YES | Stencil design + SPI plan | — | Low | Open
A-06 | PROC-06 | Per-part MSL list + J-STD-033 handling plan | Component eng | CM | TBD | TBD | Pre-proto | YES | MSL table | — | Low | Open
A-07 | PROC-09 | Footprint validation vs land patterns; dedupe library | PCB eng | — | TBD | TBD | Pre-proto | no | Footprint report | — | Low | Open
A-08 | DFA-02 | Thermal-module error-proofing + strain-gauge validation | ME | — | TBD | TBD | Pre-proto | YES | Strain test report | — | Med | Open
A-09 | DFA-03 | X-ray/SPI/MSL process controls for BGA/LGA/QFN | Quality | CM | TBD | TBD | Pre-proto | YES | Inspection plan approved | — | Low | Open
A-10 | DFA-06 | Connector load-path analysis + enclosure support | ME | — | TBD | TBD | Pre-proto | YES | Load-path calc + test | — | Med | Open
A-11 | DFT-01 | DFT bottom-side access study + boundary-scan plan | Test eng | — | TBD | TBD | Pre-pilot | YES | Coverage report | — | Med | Open
A-12 | BLD-01 | Run EVT/DVT pilot; capture KPIs | NPI | CM | TBD | TBD | Pre-vol | YES | Pilot report + pareto | — | Med | Open
A-13 | DOC-01 | Reconcile schematic/PCB/BOM/P&P baseline revisions | PLM | — | TBD | TBD | Pre-fab | no | Reconciliation record | — | Low | Open
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S1] BOM PORTATILE_1_1_BOM_NEW_DEF.ods · [S2] NC drill — plated (tool table) · [S4] Field-solver stack-up/material · [S5] Placement list (X/Y/side/mount) · [S6] ODB++ CAD netlist (access pts)
Standards: IPC-6012 · IPC-7095 · IPC-4761 · IPC-7525 · J-STD-033
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 21. Supplier Sign-Off
Supplier Sign-Off (required before release)
Written acceptance from the fabricator and CM is a release prerequisite. All currently OPEN.
Item | Owner org | Required acceptance | Status | Signature / date
Stack-up & material grade | PCB fab | Buildable to impedance & thickness | OPEN
Aspect ratio 8:1 / via-in-pad | PCB fab | Within qualified process | OPEN
Surface finish | PCB fab | Supported & recommended | OPEN
Panel & coupons | PCB fab/CM | Panel accepted | OPEN
Min trace/space & annular ring | PCB fab | Within capability | OPEN
Stencil & paste process | CM | Area ratios accepted | OPEN
MSL handling | CM | J-STD-033 plan accepted | OPEN
X-ray / ICT / FT plan | CM/test | Coverage accepted | OPEN
No supplier has yet accepted this design. This alone prevents any fabrication/production release disposition.
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S2] NC drill — plated (tool table) · [S4] Field-solver stack-up/material · [S10] Copper Gerber set 1-Top…10-Bottom
Standards: IPC-6012 · IPC-A-600 · IPC-7525
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).

## 22. Final Gate
Final Gate Approval
Conditional dispositions from the Executive Decision sheet. Signatures open — this is a preliminary screening, not a release.
Gate | Disposition | Approver (role) | Signature | Date
Engineering prototype (design) | CONDITIONAL | Lead PCB engineer
PCB quotation-ready | NO | PCB fab lead
PCB fabrication-ready | NO | PCB fab lead + PCB eng
PCBA prototype process | CONDITIONAL | CM process eng
Pilot production | NO | NPI + Quality
Volume production | NO | Program management
This package authorises NO production release. It authorises closure work toward an engineering prototype only, subject to the pre-build blockers (Executive Decision sheet).
◾ EVIDENCE & CITATIONS — this sheet's conclusions are based on:
Design sources: [S13] Evidence-recovery memo (OCR) · [S14] DFM/DFA reviews
See '0. References & Citations' for the full standards list and source-data provenance (internal storage locations omitted).